RPA BUSINESS CASE

Customs Documentation Completeness Check Automation

Automation Anywhere RPA Implementation Proposal

| Document Title | RPA Business Case, Customs Documentation Completeness Check Automation |
| --- | --- |
| Version | 1.0 |
| Status | Final |
| Prepared By | N M Ziyaf, Supply Chain Business Analyst |
| Date | June 2025 |
| Platform | Automation Anywhere, CargoWise One ERP |
| Related Document | Customs Documentation Workflow, Gap Analysis BRD v1.0 |

This business case was developed following gap analysis findings documented in the Customs Documentation Workflow BRD. It proposes RPA automation as the implementation mechanism for the pre-submission validation checkpoint identified as Gap G2 in that analysis. All data is based on replicated scenarios from real freight forwarding operations and has been anonymised for portfolio use.

1.  Executive Summary

This business case proposes the deployment of an RPA bot using Automation Anywhere to automate the customs documentation completeness check within the CargoWise One freight forwarding workflow. The automation directly addresses Gap G2 identified in the Customs Documentation Workflow Gap Analysis BRD, which found that no pre-submission validation checkpoint existed to catch documentation errors before they reached brokers and customs authorities.

The current manual process requires an operations staff member to individually retrieve each shipment record, check document completeness from memory, and assemble a documentation package before submission. This process is inconsistent, time-consuming, and responsible for approximately 12 percent of shipments experiencing documentation-related errors that result in clearance delays of 2.4 days on average.

The proposed RPA solution automates the completeness check end to end. The bot monitors CargoWise One for new booking confirmations, extracts shipment and document data, runs a rule-based completeness check against a predefined document matrix, logs results directly in CargoWise One, and only escalates to the operations team when an exception is identified. Based on current shipment volumes and time studies, the solution is projected to deliver a return on investment within seven months of go-live.

| Metric | Current State | Post-Automation Target |
| --- | --- | --- |
| Manual check time per shipment | Approximately 18 minutes | Less than 1 minute (exception handling only) |
| Documentation error rate | Approximately 12% | Less than 3% |
| Shipments requiring rework | Approximately 35% | Less than 5% |
| Estimated weekly manual effort | Approximately 18 hours | Less than 2 hours |
| Projected ROI timeline | Not applicable | 7 months post go-live |

2.  Problem Statement

2.1  Current Process Pain Points

The customs documentation completeness check is performed manually by operations staff for every shipment processed through the freight forwarding operation. Based on the gap analysis conducted in June 2025 and documented in the related BRD, the following pain points were identified and quantified.

The check relies entirely on individual operator knowledge of required document sets, which varies by shipment type, origin, destination, and commodity. There is no system-enforced checklist and no validation step within CargoWise One that prevents an incomplete documentation package from being submitted externally. As a result, approximately 12 percent of shipments are submitted with missing or incorrect documentation, triggering broker rejections, customs holds, and rework cycles that average 2.4 days of additional clearance time per affected shipment.

The manual check also consumes significant operational time. Time studies conducted during the gap analysis estimated an average of 18 minutes per shipment for a complete check, inclusive of retrieving the record, reviewing attached documents, cross-checking against shipment details, and assembling the outgoing package. Across the shipment volumes processed, this equates to approximately 18 hours of operational staff time per week dedicated to a process that is fundamentally rule-based and repeatable.

2.2  Why RPA is the Right Solution

The customs documentation completeness check meets all four criteria that make a process well-suited for RPA automation. The process is highly rule-based and follows a consistent logic that can be codified without exception handling complexity. It is high volume and repetitive, executing identically for every shipment regardless of operator. It operates within a structured digital environment, CargoWise One, which provides accessible data through its interface and API layer. And it is time-sensitive, as delays in the check directly delay submission and clearance.

An RPA solution implemented using Automation Anywhere can replicate the human check steps end to end, applying the document matrix rules consistently across 100 percent of shipments without variation, fatigue, or oversight gaps. The bot executes in seconds rather than minutes, logs every check outcome directly in CargoWise One for auditability, and only surfaces exceptions to the operations team when a genuine gap is identified.

3.  Proposed RPA Solution

3.1  Solution Overview

The proposed solution is an Automation Anywhere attended or unattended bot deployed within the existing CargoWise One environment. The bot operates continuously during business hours, monitoring for new shipment booking confirmations and executing the completeness check workflow automatically for each new booking without requiring any operator trigger.

The bot executes the following sequence for every shipment. It monitors CargoWise One for new booking confirmations triggered by the milestone event. It extracts the shipment record data including shipment type, origin, destination, commodity, and incoterms. It identifies the required document set for that shipment profile from the document matrix rules configured within the bot. It checks each required document against the attachments on the CargoWise One shipment record. If all required documents are present and the shipment details are consistent, it logs a validation pass against the record and triggers the pre-submission checkpoint clearance. If any document is missing or a discrepancy is detected, it generates an exception task assigned to the responsible operator with a two-hour resolution SLA, consistent with Requirement FR-006 from the Gap Analysis BRD.

3.2  Process Maps

The current state and future state process maps are provided as separate files in this repository. The current state map documents the manual process as it was operating prior to the proposed automation, including the identified pain points and rework loops. The future state map shows the redesigned process with RPA automation touchpoints marked, demonstrating where the bot replaces manual steps and where the operations team retains involvement for exception handling and final submission.

Refer to process_map_current_state.svg and process_map_future_state.svg in this repository.

3.3  Document Matrix — Bot Validation Rules

The bot applies a predefined document matrix to determine the required document set for each shipment. The matrix is configurable and maintained by the system administrator, allowing updates without redeployment of the bot logic.

| Shipment Type | Required Documents | Additional Conditions |
| --- | --- | --- |
| Import, General Cargo | Commercial invoice, packing list, bill of lading, customs entry form | Country of origin certificate required if preferential tariff claimed |
| Import, Dangerous Goods | Commercial invoice, packing list, bill of lading, customs entry form, dangerous goods declaration, MSDS | Packaging certificate required for certain UN classes |
| Export, General Cargo | Commercial invoice, packing list, bill of lading, export declaration | Certificate of origin required if destination country requires it |
| Export, Controlled Goods | Commercial invoice, packing list, bill of lading, export declaration, export permit | End user certificate required where applicable |
| Transshipment | Commercial invoice, packing list, master bill of lading, house bill of lading, transit declaration | Additional port authority documents where required by routing |

4.  Cost Benefit Analysis

4.1  Implementation Costs

| Cost Item | Description | Estimated Cost |
| --- | --- | --- |
| RPA Bot Development | Automation Anywhere bot design, development, testing, and deployment by RPA developer | AUD 12,000 |
| UAT and Go-Live Support | Business Analyst and System Administrator time for UAT coordination, defect resolution, and go-live support | AUD 3,500 |
| Automation Anywhere Licence | Unattended bot licence for production environment, annual cost | AUD 8,000 per year |
| CargoWise Integration Review | System Administrator review of CargoWise One data access configuration for bot | AUD 1,500 |
| Training and Change Management | Operations team briefing and updated SOP documentation | AUD 800 |
| Total Year 1 Cost |  | AUD 25,800 |
| Annual Recurring Cost (Year 2 onwards) | Licence renewal and maintenance | AUD 9,500 per year |

4.2  Projected Benefits

| Benefit Area | Basis of Calculation | Estimated Annual Value |
| --- | --- | --- |
| Operational time saving | Reduction from 18 hours to 2 hours per week of manual check time. 16 hours per week at AUD 35 per hour average operations staff rate. | AUD 29,120 |
| Rework cost reduction | Reduction from 35 percent to 5 percent of shipments requiring rework. Estimated 1.5 hours rework per shipment at AUD 35 per hour, across estimated shipment volumes. | AUD 18,200 |
| Clearance delay cost avoidance | Reduction of 2.4 day average delay on affected shipments. Storage and demurrage cost avoidance estimated at AUD 180 per day per shipment. | AUD 14,400 |
| Client retention value | Reduced complaint rate from documentation errors, estimated to protect approximately 3 percent of annual revenue at risk from repeat errors. | AUD 22,000 |
| Total Estimated Annual Benefit |  | AUD 83,720 |

4.3  Return on Investment

| ROI Metric | Value |
| --- | --- |
| Total Year 1 Investment | AUD 25,800 |
| Total Year 1 Benefit | AUD 83,720 |
| Net Year 1 Benefit | AUD 57,920 |
| ROI (Year 1) | 224 percent |
| Payback Period | Approximately 3.7 months |
| 3-Year Net Benefit (after all costs) | AUD 202,660 |

5.  Risk Assessment

| # | Risk | Description | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R1 | Document matrix incomplete | Bot flags false positives if the document matrix does not cover all shipment profile combinations | Medium | High | Comprehensive matrix review conducted before bot deployment. Operations team signs off on matrix completeness. |
| R2 | CargoWise One data access changes | System updates to CargoWise One could affect bot data access paths and cause failures | Low | High | Bot built with resilience checks. System Administrator notified before any CargoWise One updates. |
| R3 | Operator resistance to automation | Operations staff may be reluctant to trust bot validation outputs initially | Medium | Medium | Change management briefing included in implementation plan. Parallel run period planned for first two weeks post go-live. |
| R4 | Bot handling edge cases incorrectly | Unusual shipment profiles not covered by matrix rules may be misclassified | Low | Medium | All unrecognised shipment profiles escalated to operator by default. No silent failures permitted. |
| R5 | Licence cost increase | Automation Anywhere licence costs may increase at renewal | Low | Low | Annual licence cost reviewed against benefit realisation at each renewal. Alternative platforms assessed if cost exceeds threshold. |

6.  Implementation Approach

6.1  Implementation Phases

| Phase | Activity | Owner | Duration |
| --- | --- | --- | --- |
| Phase 1, Discovery | Document matrix finalisation and CargoWise One data mapping. RPA developer briefing and bot design sign-off. | BA with System Administrator | 1 week |
| Phase 2, Development | Automation Anywhere bot development covering monitoring, data extraction, rule application, logging, and exception escalation. | RPA Developer | 2 weeks |
| Phase 3, Testing | Bot testing in CargoWise One UAT environment across all shipment types in the document matrix. Defect resolution. | RPA Developer with BA | 1 week |
| Phase 4, Parallel Run | Bot runs alongside manual process for two weeks. Results compared to validate accuracy before manual process is retired. | Operations Team with BA | 2 weeks |
| Phase 5, Go-Live | Manual completeness check retired. Bot operates as primary validation mechanism. Operations team handles exceptions only. | System Administrator | 1 day |
| Phase 6, Review | 30-day post go-live review of bot accuracy, exception rate, and time savings against projected benefits. | BA | Ongoing |

6.2  Success Criteria

The implementation will be considered successful when the following criteria are met at the 30-day post go-live review.

- Bot validation accuracy is greater than 97 percent across all shipment types processed

- Documentation error rate has reduced from 12 percent to less than 3 percent of shipments

- Manual completeness check effort has reduced from 18 hours to less than 2 hours per week

- Zero silent bot failures — all unrecognised profiles are correctly escalated to the operations team

- Operator satisfaction with the exception handling workflow is rated satisfactory or above in post-go-live feedback

7.  Recommendation and Decision

Based on the gap analysis findings from the Customs Documentation Workflow BRD, the cost benefit analysis in this document, and the risk assessment above, I recommend proceeding with the Automation Anywhere RPA implementation as proposed.

The process is a strong automation candidate, the financial case is compelling with a 3.7-month payback period and 224 percent first-year ROI, and the risk profile is manageable with the mitigations outlined. The parallel run approach in Phase 4 provides a low-risk transition path that maintains operational continuity while confidence in the bot is established.

Approval is sought to proceed to Phase 1 Discovery and to commission the RPA developer engagement.

| Decision | Approver | Date | Signature |
| --- | --- | --- | --- |
| Proceed with RPA implementation as proposed | Operations Manager |  |  |
| Budget approval for Year 1 investment of AUD 25,800 | Finance Director |  |  |

8.  Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 0.1 | June 2025 | N M Ziyaf | Initial draft following BRD gap analysis completion |
| 0.2 | June 2025 | N M Ziyaf | Cost benefit analysis and risk assessment added |
| 1.0 | June 2025 | N M Ziyaf | Final version with all sections complete |

Prepared by N M Ziyaf, Supply Chain Business Analyst   |   linkedin.com/in/ziyafmohamed   ß